## ProjCrashing
CHAPTER 3: Example 12
Project Management |  |  | Crashing
Results
Data |  |  |  | Normal time | 15 | [5 empty] | Minimum crash cost to meet project goal | 0
Project goal | 13 |  |  | Minimum time | 7 | [5 empty] | Project time
[5 empty] | Immediate Predecessors (1 per column) | [5 empty] | Intermediate Computations
Activity | Normal Time | Normal Cost | Crash Time | Crash Cost | Pred 1 | Pred 2 | Pred 3 | Pred 4 |  | Crash days | Crash cost/day | Crash limit
A | 2 | 22000 | 1 | 22750 | [5 empty] | 0 | 750 | 1
B | 3 | 30000 | 1 | 34000 | [5 empty] | 0 | 2000 | 2
C | 2 | 26000 | 1 | 27000 | A |  |  |  |  | 0 | 1000 | 1
D | 4 | 48000 | 3 | 49000 | A | B |  |  |  | 0 | 1000 | 1
E | 4 | 56000 | 2 | 58000 | C |  |  |  |  | 0 | 1000 | 2
F | 3 | 30000 | 2 | 30500 | C |  |  |  |  | 0 | 500 | 1
G | 5 | 80000 | 2 | 84500 | D | E |  |  |  | 0 | 1500 | 3
H | 2 | 16000 | 1 | 19000 | F | G |  |  |  | 0 | 3000 | 1
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
[10 empty] | 0 | 0 | 0
Precedence computations | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
1 if col precedes row | A | B | C | D | E | F | G | H | xxxxx | xxxxx | xxxxx | xxxxx | xxxxx | xxxxx | xxxxx | xxxxx | xxxxx | xxxxx | xxxxx | xxxxx | xxxxx | xxxxx | xxxxx | xxxxx | xxxxx
A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
H | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
xxxxx | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
xxxxx | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
xxxxx | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
xxxxx | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
xxxxx | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
xxxxx | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
xxxxx | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
xxxxx | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
xxxxx | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
xxxxx | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
xxxxx | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
xxxxx | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
xxxxx | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
xxxxx | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
xxxxx | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
xxxxx | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
xxxxx | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Normal time | 2 | 3 | 2 | 4 | 4 | 3 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TimeFinish (variable) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
crash days (variable) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
limit | 1 | 2 | 1 | 1 | 2 | 1 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project time | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Crash days | A: Finish Times for Tasks must be greater than finish for all predecessors; B: Finish A + T(row)-crash row; C: Finish B + T(row)-crash row; D: Finish C + T(row)-crash row; E: Finish D + T(row)-crash row; F: Finish E + T(row)-crash row; G: Finish F + T(row)-crash row; H: Finish G + T(row)-crash row; xxxxx: Finish H + T(row)-crash row; xxxxx: Finish I + T(row)-crash row; xxxxx: Finish J + T(row)-crash row; xxxxx: Finish K + T(row)-crash row; xxxxx: Finish C + T(row)-crash row
0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
0 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
0 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Data
| Time | Precedence 1 | Precedence 2 | Precedence 3 | Precedence 4
A | A: 2; B: 0; C: 0; D: 0; E: 0
B | A: 3; B: 0; C: 0; D: 0; E: 0
C | A: 2; B: A; C: 0; D: 0; E: 0
D | A: 4; B: A; C: B; D: 0; E: 0
E | A: 4; B: C; C: 0; D: 0; E: 0
F | A: 3; B: C; C: 0; D: 0; E: 0
G | A: 5; B: D; C: E; D: 0; E: 0
H | A: 2; B: F; C: G; D: 0; E: 0
Results
Task | A: Early Start; B: Early Finish; C: Late Start; D: Late Finish; E: Slack
A | A: 0; B: 2; C: 0; D: 2; E: 0; G: 0; H: 0; xxxxx: 0; xxxxx: 0; xxxxx: 0
B | A: 0; B: 3; C: 1; D: 4; E: 1; G: 0; H: 0; xxxxx: 0; xxxxx: 0; xxxxx: 0
C | A: 2; B: 4; C: 2; D: 4; E: 0; G: 0; H: 0; xxxxx: 0; xxxxx: 0; xxxxx: 0
D | A: 3; B: 7; C: 4; D: 8; E: 1; G: 0; H: 0; xxxxx: 0; xxxxx: 0; xxxxx: 0
E | A: 4; B: 8; C: 4; D: 8; E: 0; G: 0; H: 0; xxxxx: 0; xxxxx: 0; xxxxx: 0
F | A: 4; B: 7; C: 10; D: 13; E: 6; G: 0; H: 0; xxxxx: 0; xxxxx: 0; xxxxx: 0
G | A: 8; B: 13; C: 8; D: 13; E: 0; G: 0; H: 0; xxxxx: 0; xxxxx: 0; xxxxx: 0
H | A: 13; B: 15; C: 13; D: 15; E: 0; G: 0; H: 0; xxxxx: 0; xxxxx: 0; xxxxx: 0
[7 empty] | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 | 0
| Project | 15 |  |  |  |  | 0 | 0 | 0 | 0 | 0
Early start computations | G: 0; H: 0
A | B: 0; C: 0; D: 0; E: 0
B | B: 0; C: 0; D: 0; E: 0
C | B: 2; C: 0; D: 0; E: 0
D | B: 2; C: 3; D: 0; E: 0
E | B: 4; C: 0; D: 0; E: 0
F | B: 4; C: 0; D: 0; E: 0
G | B: 7; C: 8; D: 0; E: 0
H | B: 7; C: 13; D: 0; E: 0
Late finish computations
| A | B | C | D | E | F | G | H
A | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
B | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
C | 2 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
D | 4 | 4 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
E | 15 | 15 | 4 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
F | 15 | 15 | 10 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
G | 15 | 15 | 15 | 8 | 8 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
H | 15 | 15 | 15 | 15 | 15 | 13 | 13 | 15 | 15 | 15 | 15 | 15 | 15
| 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
| 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
| 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
| 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
| 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
| 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
| 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
| 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
| 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
| 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
| 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
| 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
| 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
| 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
| 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
| 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
| 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
| 2 | 4 | 4 | 8 | 8 | 13 | 13 | 15 | 15 | 15 | 15 | 15 | 15
Project Management
Data
| Time | Precedence 1 | Precedence 2 | Precedence 3 | Precedence 4
A | 1 | 0 | 0 | 0 | 0
B | 1 | 0 | 0 | 0 | 0
C | 1 | A | 0 | 0 | 0
D | 3 | A | B | 0 | 0
E | 2 | C | 0 | 0 | 0
F | 2 | C | 0 | 0 | 0
G | 2 | D | E | 0 | 0
H | 1 | F | G | 0 | 0
Results | D: 7
Task | Early Start | Early Finish | Late Start | Late Finish | Slack
A | 0 | 1 | 0 | 1 | 0
B | 0 | 1 | 0 | 1 | 0
C | 1 | 2 | 1 | 2 | 0
D | 1 | 4 | 1 | 4 | 0 |  | 3 | 1
E | 2 | 4 | 2 | 4 | 0
F | 2 | 4 | 4 | 6 | 2
G | 4 | 6 | 4 | 6 | 0
H | 6 | 7 | 6 | 7 | 0
| Project | 7
Early start computations
A | B: 0; C: 0; D: 0; E: 0
B | B: 0; C: 0; D: 0; E: 0
C | B: 1; C: 0; D: 0; E: 0
D | B: 1; C: 1; D: 0; E: 0
E | B: 2; C: 0; D: 0; E: 0
F | B: 2; C: 0; D: 0; E: 0
G | B: 4; C: 4; D: 0; E: 0
H | B: 4; C: 6; D: 0; E: 0
Late finish computations
| A | B | C | D | E | F | G | H
A | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
B | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
C | 1 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
D | 1 | 1 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
E | 7 | 7 | 2 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
F | 7 | 7 | 4 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
G | 7 | 7 | 7 | 4 | 4 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
H | 7 | 7 | 7 | 7 | 7 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
| 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
| 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
| 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
| 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
| 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
| 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
| 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
| 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
| 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
| 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
| 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
| 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
| 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
| 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
| 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
| 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
| 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
| 1 | 1 | 2 | 4 | 4 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
Enter the data in the shaded area. Then go to the DATA Tab on the ribbon, click on Solver in the Data Analysis Group and then click SOLVE. If SOLVER is not on the Data Tab then please see the Help file (Solver) for instructions.